## Milestones & Owners
Milestone | Detail (Items with * have template at CatholicFSMN.org/Endow-Toolkit) | Responsible | Accountable | Consulted | Informed | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep
Planning & Purpose |  | TIP: Remember to only have ONE person in Responsible & ONE person in Accountable columns.
| Amount to Endow Goal Set | Trustee | Priest | Finance Council, Bookkeeper | All parish employees
| Endowment Purpose & Restrictions | Trustee | Priest | Finance Council, Bookkeeper | All parish employees
Successor Benefeciary
Spending Policy*
Campaign Budget
Secure Outside and/or Volunteer Help*
Edit & Populate the timeline & RACI (below)
| Documentation & Filing | Secretary |  |  | Finance Council, Bookkeeper
Documentation | Foundation Endowment Account Established*
Access to Monthly Statements
Fundraise - Case Statement | Create Case Statement* | John on Finance Council | Trustee | Pastoral Council, a Few Major donors?
Fundraise - Major Donors* | Gift Instrument Created & Legally Reviewed*
Reviewed giving history & identified potential major donors
Set leadership goal
Scheduled meetings
Prepared materials
Held conversations
Documented Responses
Followed up & Confirmed gifts
Established matching gifts (if applicable)
Fundraise - Planned Giving* | Set date with the Foundation*
Prepare for hosting as needed
Host planned giving seminars
Follow up with attendees afterwards
Fundraise - Mass Fundraising* | Campaign communication plan (tips here: CatholicFSMN.org/CommsPlan )*
Create fundraising materials*
Mail, publish, share, etc.
Add more detail here once you have the comms plan created
Protect & Grow | Acknowledge each gift with a thank you card or letter
Tax receipt each gift
Transfer gifts to the Foundation at predetermined cadence*
Report to parish on progress using monthly Foundation statements*

## Resources
More Info on How to Use a RACI (Responsible, Accountable, Consulted, Informed):
https://project-management.com/understanding-responsibility-assignment-matrix-raci-matrix/
*Some parishes may wish to establish a legal endowment which will require more robust documentation and establishment of a formal Board. We encourage you to consult your lawyer to determine whether a formal legal endowment is a priority for your parish.